## Sheet1
Test case nr:	Expected result	Actual result	Tester's name and date	Fixed?
RQ-001-Customer	App handles multiple users without mistake	app handles multiple users, separate profile	Teemu Antila 10.12.2024
RQ-001b-Customer	No limits on user registrations	No known limit on userregeistration limit	Teemu Antila 10.12.2024
RQ-003-Customer	Employee Unique ID generated automatically	Eployee Unique ID and worker is generated automaticaly	Teemu Antila 10.12.2024
RQ-003b-Customer	Employee detaisl added manualy	Employee details added manually, and are stored in the database	Teemu Antila 10.12.2024
RQ-004-customer	Employee work hours logger automatically	Employee work hours logged automaticaly uppon login until logout	Teemu Antila 10.12.2024	Employees must logout from the website the website also starts logging workhours automaticaly, not project breaking, but can be improved on. Dev: Teemu Antila
RQ-004b-Customer	Allows to be loged in with Qr code (work in progress
RQ-004c-Customer	The app generates files to be downloaded containing work hours for daily / Weekly / Monthly, summarizing work time respectively, while contains employee title aswell	The app generates files to be downloaded containing work hours for daily / Weekly / Monthly, summarizing work time respectively, while the title column is there the Title is inaccessible for somereason.	Teemu Antila 10.12.2024	For some reason the title is inaccessible even on the admin dashboard activity logs, and within the user profile own activiti logs. However the title displays on profile and in the admin's own employee details wiev. Dev Janos Erdös
RQ-005-Customer	The work logs have the date and time logging the work hours for every day automaticaly handling upon login	The users should logout everytime to log their work hours.	Teemu Antila 10.12.2024	It could be improved for manually starting shift, on the app side we will try to look into this deeper Dev: Teemu Antila & Janos Erdös
RQ-006-Customer	Employee information will be compiled on a website, where you can check more detailed information	Admin can wisit "Admin Dashboard" where every employees data is visible to the admin ( except the password)	Teemu Antila 10.12.2024	Admin should have access to the users password in case someone forgets it providing a replacement from only the Admin. For now not pproject breaking but something to improve on. Dev: Teemu Antila
RQ-002-DEV	Database is set up to handle user data and details when registered. The DB stores epmployees work hours and it is accessible	Database is set up to handle user data and details when registered. The DB stores epmployees work hours and it is accessible	Teemu Antila & Janos Erdös 10.12.2024
RQ-002b-DEV	Creating a website for the server as a User Interface. Admin and employees side separate.	Creating a website for the server as a User Interface. Admin and employees side separate. The web sites are accessible respectively. Eployees don't have access to to other employees profiles	Teemu Antila & Janos Erdös 10.12.2024
RQ-003-DEV	User interface generated, responds well	User interface is responsive tough it looks a little too simple	Janos Erdös 16.12.2024
RQ-004-DEV	New users can be resgistered, both the main website and the admin can register new users	New users can be resgistered, both the main website and the admin can register new users, registration is straightforward. It does not send e-mail veryfication, nor any e-mail as of the user registered whatsoever.	Janos Erdös 16.12.2024
RQ-004-DEVb	Simplified and Unique employee ID generation is implemented	Simplified and Unique employee ID generation is implemented	Janos Erdös 16.12.2024
RQ-004-DEVc	Srores information correctly given by employees	Srores information correctly given by employees	Janos Erdös 16.12.2024
RQ-005-DEV	App prooved to communicate with server on failing mann times to request login	The app prooved that it communicates with the server by showing the serverside logging in the "CMD" resulting in failing to login	Janos Erdös 16.12.2024	Fixed issue where loging in is impossible by the next requirement DEV: Janos Erdös & Teemu Antila
RQ-006-DEV	The Server and the companion app shuld communicate ( retrieving data for user profiles, and sending request to login, starting clock, and logout with sending data pack to the logs	The Server and the companion app shuld communicate ( retrieving data for user profiles, and sending request to login, starting clock, and logout with sending data pack to the logs	Janos Erdös 16.12.2024
RQ-007-DEV	Qr-code Generated by Python the source for it is located in the repo's root directory "QR_code.py"	Further test may be required, but i trust the QR -code hardcoded locations will be working as intended	Janos Erdös 16.12.2024	Unable to test the QR-code other than my home location where it works flawlessly DEV: Janos Erdös
RQ-008-DEV	QR-code starts the worktime (clock) and measures in format of hh:mm:ss	QR-code starts the worktime (clock) and measures in format of hh:mm:ss	Janos Erdös 16.12.2024
RQ-009-DEV	Loging out of the Companion app results as sending the time measured as data to the server, ensuring the logs are updated	Loging out of the Companion app results as sending the time measured as data to the server, ensuring the logs are updated	Janos Erdös 16.12.2024
RQ-010-DEV-Extra-Feature	On the web page profile and in Admin Dashboard, there are work logs available to download in a ".csv" format (excell opens it) Summarizing work logs as follow: Daily, Weekly, Monthly	On the web page profile and in Admin Dashboard, there are work logs available to download in a ".csv" format (excell opens it) Summarizing work logs as follow: Daily, Weekly, Monthly (Could be better on reading the data, not too user frienly yet and the title is not accessed by the logs also)	Janos Erdös 16.12.2024	For the purpose of the evaluation as of now we leave it as is. DEV: Janos Erdös & Teemu Antila
SPEC-001-REQ-TESTERCASE	New "employee" have tested the companion app Anita Papp	Easy to understand userfriendly, seems to be working well. Takes a little while to load, i am unused to the loading time it takes to communicate with the "Server?" . I asume.	Anita Papp 16.12.2024	Serverside responsive times are a little long, users might have to get acustomed to it. I think it is because of the "Loop connection " - Using remote access on the server as it is hosted on the laptop. DEV: Janos Erdös